60-Day Thesis Completion Workflow

+ 15-Day Manuscript & Journal Submission Plan

PINN-based Coupled Hydro-Mechanical Slope Stability Analysis of an Open-Pit Mine

Abrar Mahir  ·  Reg. 2020336031

Dept. of Petroleum & Mining Engineering, SUST

Target: Q1 journal (Computers and Geotechnics / Engineering Geology)

Hardware assumptions baked into this plan

Laptop — “WhiteShadow”: Intel i5-1135G7, 8 GB RAM, NVIDIA MX450 (2 GB VRAM). Treated as a development & writing machine only. It cannot run your full-scale training (2 GB VRAM + 8 GB RAM is far below the 8–16 GB needed for an 8-layer coupled PINN with second-order AD at N_PDE up to 50,000).

Lab PC: assumed to have a proper NVIDIA GPU (≥8 GB VRAM). All training, SSR sweeps, and sensitivity runs live here. If its GPU is weaker than assumed, the training-day counts below stretch — tell me the model and I’ll recalibrate.

# Contents

Contents	2

How to read this plan	3

The 60 days at a glance	4

Days 1–9 — Environment & Data Derivation (Phase 0 + Phase 1)	5

Days 10–14 — Domain, Boundary & Initial Conditions (Phase 2)	7

Days 15–24 — Build the PINN (Phase 3)	8

Days 25–38 — Full Training & Validation (Phase 4)	10

Days 39–48 — SSR Factor of Safety: MC vs GHB (Phase 5)	12

Days 49–56 — Sensitivity, Ablation & Figures (Phase 6a)	13

Days 57–60 — Buffer & Thesis Assembly	14

Days 61–75 — Manuscript & Journal Submission (15 days)	15

Practical notes for the two-machine setup	17

Keep the two machines in sync with Git	17

Working while the GPU runs	17

What the laptop genuinely cannot do — and the workaround	17

Risk buffers — where the plan can absorb slippage	17

# How to read this plan

This document re-casts your existing six-phase roadmap (Steps 1.1–6.3) as a working calendar. Nothing in the underlying science changes; what changes is sequencing, realistic daily granularity, and a hard split between what your laptop can do and what must wait for the lab PC. The 60 days carry you from a blank environment to a fully validated result set. The following 15 days turn that result set into a submitted manuscript.

Days are working days. If you work weekends, the calendar compresses; if you take one rest day a week, add roughly two calendar weeks. Buffer days are built in deliberately — PINN training fails in ways you cannot predict, and a plan with no slack is a plan that slips.

The colour in the rightmost column of every table tells you where the work happens:

| LAPTOP | Runs fine on WhiteShadow. Writing, data prep, derivations, code authoring, debugging at toy scale, figure assembly, post-processing of results already computed. |
| --- | --- |
| LAB PC | Must run on the high-end GPU. All full-scale PINN training, the SSR factor-of-safety sweeps, and every sensitivity/ablation run. |
| EITHER | Light enough for the laptop, but faster on the lab PC if it’s free — e.g. quick validation reruns, small parameter checks. |

The golden rule for your setup: write code on the laptop, run it on the lab PC. Keep a single Git repository so the two machines stay in sync; never edit code directly on the lab PC during a run.

# The 60 days at a glance

| Day | Task & detail | Run on |
| --- | --- | --- |
| 1–9 | Phase 0 + Phase 1 — Environment, repo, and the data-derivation pipeline. Almost entirely laptop work. | Mostly laptop |
| 10–14 | Phase 2 — Computational domain, boundary conditions, initial state. | Laptop |
| 15–24 | Phase 3 — Build the PINN: architecture, loss function, non-dimensionalisation, training scaffold. Author on laptop, smoke-test on lab PC. | Laptop + Lab PC |
| 25–38 | Phase 4 — Full training: baseline HM, convergence, validation against analytical solution. Heaviest GPU phase. | Lab PC |
| 39–48 | Phase 5 — SSR factor-of-safety: MC and GHB sweeps, failure-surface extraction. | Lab PC |
| 49–56 | Phase 6a — Sensitivity & ablation runs, then results figures. | Lab PC → Laptop |
| 57–60 | Buffer + thesis-document assembly and internal review. | Laptop |

# Days 1–9 — Environment & Data Derivation (Phase 0 + Phase 1)

Goal of this block: a clean, reproducible toolchain on both machines, and a complete, self-consistent SI parameter set for every geological stratum of Section 5-5′. Your roadmap is explicit that this is the most error-prone phase of the whole project — a single wrong unit here propagates silently into every later result. Treat slowness here as an investment.

Why this is laptop work: nothing here touches the GPU. It is unit conversions, pedotransfer functions, spreadsheet bookkeeping, and short SciPy scripts — all trivially within an i5 and 8 GB of RAM.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 1 | Environment setup — laptop Install Python 3.10, create a conda/venv environment, install PyTorch (CPU build is fine here), NumPy, SciPy, Matplotlib, and Rosetta3. Initialise a Git repository and push to GitHub/GitLab. Set up the identical environment file (environment.yml) you will replicate on the lab PC. | LAPTOP |
| 2 | Environment setup — lab PC + GPU sanity check Clone the repo, recreate the environment with the CUDA PyTorch build. Run a 30-second GPU test: torch.cuda.is_available(), a tiny tensor matmul, and one toy second-order autograd call with create_graph=True. Confirm CUDA version matches the PyTorch build. This is the only lab-PC task this week. | LAB PC |
| 3 | Step 1.1 — Unit conversion to SI Convert every Ulusay et al. (2014) parameter to metres, seconds, Pascals, kg/m³. K from m/day → m/s, unit weight kN/m³ → density kg/m³, stresses MPa → Pa. Build one master spreadsheet with original value, conversion factor, and SI value side by side, per stratum. | LAPTOP |
| 4 | Step 1.2–1.3 — SWCC & elastic parameters Derive van Genuchten SWCC parameters (α, n, θ_s, θ_r) per layer using Rosetta3 from grain-size / Atterberg inputs. Derive rock-mass modulus E_rm and Poisson’s ratio ν. Record the derivation method and citation for each — reviewers will ask. | LAPTOP |
| 5 | Step 1.4 — Hoek-Brown parameters Compute m_b, s, a from GSI, σ_ci, and disturbance factor D for each rock unit. Cross-check against the values implied in the source paper. Tabulate MC equivalents (c, φ) for the comparison you will make later. | LAPTOP |
| 6 | Step 1.5 — Porosity & remaining parameters Initial porosity n₀ per layer; assemble the Kozeny-Carman reference state. Verify you can now state, for every stratum: K_s, ρ_dry, ρ_sat, E, ν, (α,n,θ_s,θ_r), (σ_ci,m_b,s,a), n₀. This is the Phase-1 completion checklist. | LAPTOP |
| 7 | Step 1.6 — Non-dimensionalisation Define characteristic scales (length, time, pressure) and produce the dimensionless forms of both PDEs so all residuals sit at O(1). This is the single most important numerical step for training stability — without it, GradNorm cannot balance loss terms differing by 10⁶. | LAPTOP |
| 8 | Verification & second pair of eyes Re-derive three parameters by hand independently and confirm they match the spreadsheet. Send the parameter table to your supervisor for a sanity check. Catching an error today costs an afternoon; catching it on Day 40 costs a week of retraining. | LAPTOP |
| 9 | Buffer / catch-up Slack for derivations that took longer, missing source values that needed chasing, or Rosetta3 install friction. If you’re ahead, start reading Phase 2. | LAPTOP |

# Days 10–14 — Domain, Boundary & Initial Conditions (Phase 2)

CORRECTED 1 Aug 2026 — Steps 2.1–2.3 were written against the wrong figure. The F = 0.94 geometry is Fig. 19d (remedial measures), not Fig. 5b (pre-mining geology). The Section 5 domain contains Tm / Mk / Mk_d only: no coal seam, no underclay, no confined aquifer. The original coal-seam and underclay conditions are correct for SECTION 7 and are retained as Step 2.2b, deferred.

Goal: define the geometry of Section 5 N, a complete boundary-condition set for both PDEs, and a physically consistent t = 0 state. The network is geometry-agnostic, so every spatial constraint enters through sampling and the loss.

Why laptop: this is geometry definition and analytical bookkeeping in NumPy — no training. Coordinate arrays, boundary-segment sampling logic, and a one-off geostatic-stress lookup. All fits comfortably in 8 GB.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 10 | Step 2.1 — 2-D computational domain (COMPLETE) Section 5 N encoded from Fig. 19d, NOT Fig. 5b. Fig. 5b is the pre-mining geological section and contains no pit face; Fig. 19d is the remedial-measures figure that carries the F = 0.94 profile. Domain: quadrilateral, x = 0–268 m from toe, z = 200–365 m a.s.l. Excavated face 31.06° (paper: '30° overall'), 61.6 m high, crest x = 102 m, toe 271.1 m a.s.l.; 21 m bench x = 102–123 m; natural ground 7–22° above; bounded upslope by fault F1 (dip 81.4°). STRATA ARE Tm / Mk / Mk_d — there is no coal seam, underclay or weak zone in this domain. Per the Fig. 5 legend: Tm = crystallized limestone (Turgut Fm., AQUIFER); Mk = medium–thick-bedded marl-limestone (Sekköy, aquiclude); Mk_d its deformed member. Ly (coal) sits 50–80 m BELOW the domain floor. The earlier 'underclay / coal seam / Sekköy marl, 400 × 170 m' description was wrong on both geometry and stratigraphy. Deliverables: geometry.py (material_tag, inside_domain), seven digitised CSVs, 09_checks.py. Digitisation precision ±0.2 m, verified four ways. | LAPTOP |
| 11 | Step 2.2a — Boundary conditions, seepage (Section 5) Natural ground (x 123–266, along z_ground): rainfall flux Neumann, q·n = 5.56e-6 m/s. Use the outward normal, not q_z — on a 31° face these differ by 14%. Bench (x 102–123, z ≈ 332.7): same flux; flat, so ponding-prone. Cut face (x 0–102): seepage face. NOT a fixed Dirichlet — the saturated portion is part of the solution. Enforce by complementarity: ψ ≤ 0, q·n ≥ 0, ψ·(q·n) = 0. Pit floor (x = 0, z 200–271.1): DECISION REQUIRED — ψ = 0 if dewatered (likely, the pit was pumped) or no-flow if treated as a symmetry cut. Affects toe uplift, where the failure surface exits. Base (z = 200, x 0–243.6): no-flow. F1 far field (x_f1(z), z 200–358): hydrostatic Dirichlet — DATUM REQUIRED, see workbook sheets 01_Fig07_HydHead and 04_Fig10a_Piezo. NO coal-seam Dirichlet and NO Nguyen–Raudkivi drawdown in this section. Note the inverted hydrogeology: the aquifer (Tm) is at the BASE, overlain by marl aquicludes — the reverse of Section 7. Implemented in boundaries.py with arc-length stratified sampling. | LAPTOP |
| 12 | Step 2.2 — Boundary conditions (mechanical) Base (z = 200): u = v = 0. F1 far field: roller, u = 0, v free. Cut face, bench and natural ground: traction-free. Body force ρ(x,z)g with ρ from material_tag. Start w_BC = 100 for GradNorm to rebalance later. Unchanged from the original plan — the mechanical BCs are geometry-driven and survive the stratigraphic correction. | LAPTOP |
| 13 | Step 2.3 — Initial conditions (Section 5) REWRITTEN. The original entry (confined head h₀ = 205 m a.s.l. in the coal seam, bedrock pressure in underclay) belongs to Section 7 — neither unit exists here, and 205 m is below the domain floor. Seepage IC: matric suction in the Mk/Mk_d marl above the water table; saturated hydrostatic in Tm below it. Water-table elevation still to be set from the head data. Mechanical IC: geostatic K₀ column. K₀ = ν/(1−ν); use each unit's own ν — the ≈0.39 marl value does not apply to Tm limestone. Precompute σ_geostatic once as a stored lookup for L_IC. | LAPTOP |
| 14 | Domain visual check + buffer Plot domain, Tm/Mk/Mk_d contacts, the 31° cut face, and a representative collocation cloud (manuscript Fig. 3). Overlay against figures/fig19d_section5.png to confirm the digitisation. Verify BC points land on the correct segments. Also close the three open items: X_MK_DIVIDE (currently assumed 90.7 m), Z_BASE (assumed 200 m, verify Tm continues that deep on Fig. 5b), and the property dictionaries in geometry.py (still placeholders — Tm is crystallized limestone, a material absent from the original Step 1.1 table). | LAPTOP |
| — | Step 2.2b — Boundary conditions, Section 7 (DEFERRED, coupled HM) The original Step 2.2 list, correct for Section 7 where the coal seam and confined aquifer are present: top rainfall flux Neumann 5.56e-6 m/s; pit face ψ = 0 seepage face; coal seam Dirichlet drawdown from the Nguyen–Raudkivi solution; far-field hydrostatic; bottom no-flow. CORRECTION before use: the coal-seam inflow is q₁ = 0.56 m³/day/m, i.e. 6.48e-6 m³/s/m — not the 0.056 printed in the paper's text, which is a typographic error (summing 0.56/√t over 30 days gives 5.368 m³/m against the paper's stated 5.37; the 0.056 version gives 0.537). Your Step 1.1 SI sheet carries the wrong value. Validation targets for Section 7: F = 1.19 initial, 0.744 and 0.707 shifting stages, 1.250 at 20°, 1.346 at 18°. | LAPTOP |

# Days 15–24 — Build the PINN (Phase 3)

Goal: a complete, runnable PINN — network, loss function, training loop, logging, checkpointing — verified to run end-to-end at toy scale before you commit GPU-days to it.

The split that matters here: you author and debug on the laptop at deliberately tiny scale (2–3 hidden layers, N_PDE ≈ 500, a few hundred epochs). At that size the MX450’s 2 GB is enough and the i5 is fine. The moment the code runs without crashing, you push to Git and smoke-test the full-size configuration on the lab PC. You do not attempt full-size training on the laptop — it will OOM.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 15 | Step 3.1 — Network architecture Implement the fully-connected feed-forward net: inputs (x*, z*, t*), 8 hidden layers, tanh activations, outputs (ψ*, u*, v*). Build it parameterised so depth/width are config flags — you’ll run it tiny on laptop, full on lab PC. | LAPTOP |
| 16–17 | Step 3.2 — Loss function (the core work) Code L_PDE (Richards + Navier-Cauchy residuals via autograd, create_graph=True), L_BC, L_IC, and the optional L_data. This is the most intricate code in the project — budget two full days. Unit-test each residual term against a known analytical case at a single point. | LAPTOP |
| 18 | Step 3.3 — Two-way coupling Wire in the monolithic coupling: Bishop effective-stress in the mechanical residual, Kozeny-Carman porosity-strain feedback into the hydraulic conductivity. Keep a config flag to disable feedback (you need the one-way run for the ablation later). | LAPTOP |
| 19 | Step 3.4 — Adaptive weighting + optimiser scaffold Implement GradNorm loss weighting and the two-stage Adam → L-BFGS protocol. Add logging (per-term losses), checkpoint save/load, and a resume-from-checkpoint path — essential for long lab-PC runs that may be interrupted. | LAPTOP |
| 20 | Toy-scale end-to-end run Run the whole pipeline on the laptop at toy scale: 2 layers, N_PDE = 500, 1,000 Adam epochs. You are not chasing accuracy — only confirming nothing crashes, losses decrease, checkpoints write and reload. Expect to find bugs here; that’s the point. | LAPTOP |
| 21 | Fix what the toy run exposed Debug whatever the toy run broke — shape mismatches, NaN gradients, exploding loss terms. Iterate fast on the laptop because the cycle is seconds, not minutes. | LAPTOP |
| 22 | First full-size smoke test — lab PC Pull the repo on the lab PC. Run the full configuration (8 layers, N_PDE = 10,000) for ~2,000 epochs only. Confirm it fits in VRAM, measure seconds/epoch to estimate full-run wall-clock, and watch the loss curve shape. Do not train to convergence yet. | LAB PC |
| 23 | Tune for the lab PC Based on the smoke test: set batch/collocation sizes to fit comfortably in VRAM with headroom, fix the learning-rate schedule, confirm GradNorm warm-up behaves. Commit the final “production” config. | LAB PC |
| 24 | Buffer Slack for coupling bugs or VRAM tuning. Phase 3 is the phase most likely to overrun — this buffer is real, not decorative. | EITHER |

# Days 25–38 — Full Training & Validation (Phase 4)

Goal: a converged baseline coupled HM solution (SRF = 1) whose pore-pressure and displacement fields are physically sensible and validated against an analytical benchmark. Everything downstream depends on this being right.

Why this is entirely lab-PC: this is the heavy compute. A full Adam (100k epochs) + L-BFGS (10–50k iters) run with second-order AD over 8 layers and tens of thousands of collocation points is exactly the workload your 2 GB MX450 cannot hold. Your laptop’s job during this block is to monitor, read logs, and write — not to compute.

A note on time: PINN training is iterative and failure-prone. You will likely train, diagnose a pathology in the loss curve, adjust weights or sampling, and retrain — possibly several times. That is why this block is 14 days for what looks like “run one script.” Budget for at least three full training cycles.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 25–27 | Production training run #1 — baseline HM Launch the full Adam → L-BFGS training to drive PDE residuals below ~10⁻⁵. Depending on the lab GPU this is hours to a couple of days of wall-clock. Use nohup/tmux or a job scheduler so it survives disconnects; checkpoint frequently. | LAB PC |
| 26–27 | In parallel, on the laptop — start writing Methodology While the GPU runs unattended, draft Manuscript §3 (Methodology) on the laptop: governing equations, coupling formulation, architecture, training protocol. You know these cold now and the text is needed regardless of results. | LAPTOP |
| 28 | Diagnose convergence Inspect the training-loss figure (total, L_PDE, L_BC, L_IC, L_data on semi-log vs epoch, with the Adam→L-BFGS handover marked — this becomes Fig. 4). Look for stalled terms, oscillation, or a loss term that never descends. | LAB PC |
| 29–31 | Retrain as needed (cycle #2) Adjust collocation sampling, GradNorm targets, or learning-rate schedule based on the diagnosis, and retrain. Treat this as expected, not as failure. Keep each run’s config and result so you can report what worked. | LAB PC |
| 32–33 | Validation against analytical solution Compare PINN piezometric-head drawdown against the Nguyen-Raudkivi analytical solution at three distances and three times (paired scatter + 1:1 line → Fig. 7). This is your proof the solver is correct, independent of the case study. | LAB PC |
| 34–35 | Baseline field inspection Generate and inspect the pore-pressure field at t = 0, 1, 7, 30 days (wetting front + drawdown cone → Fig. 5) and the baseline displacement field at SRF = 1 (→ Fig. 6). Confirm the baseline is elastic, not already failing. | LAB PC |
| 36–37 | Final production run + freeze baseline One clean, fully-converged run with the settled configuration. Archive the checkpoint and all field outputs — this frozen baseline is the input to every SSR and sensitivity run. Tag it in Git. | LAB PC |
| 38 | Buffer Slack for a stubborn convergence problem. If training fought you, you’ll be glad of this; if not, push ahead into Phase 5. | EITHER |

# Days 39–48 — SSR Factor of Safety: MC vs GHB (Phase 5)

Goal: the headline scientific result — FOS for Section 5-5′ under both Mohr-Coulomb and Generalized Hoek-Brown, plus the critical failure surfaces extracted automatically from the shear-strain field. This is the novelty your whole thesis is built around.

Why lab-PC: SSR is a sweep — you re-solve (or fine-tune from the frozen baseline) at a sequence of strength-reduction factors, watching for the SRF at which the PDE loss refuses to converge. That is many training-scale solves in series. The post-processing (γ_max heat-maps, vector plots) is light and can come back to the laptop.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 39–41 | Step 5.1 — MC-SSR sweep Sweep SRF upward, fine-tuning the PINN from the frozen baseline at each step. The critical SRF where L_PDE flatlines high / displacement gradients blow up is FOS_MC. Bracket it, then bisect for precision. Expect agreement within 5–10% of the paper’s LEM F. | LAB PC |
| 42–44 | Step 5.2 — GHB-SSR sweep Repeat the sweep with the Generalized Hoek-Brown criterion. This requires the GHB strength-reduction formulation (reducing m_b, s appropriately rather than c, φ). Obtain FOS_GHB. The MC-vs-GHB difference is your publishable result. | LAB PC |
| 45 | SSR convergence figure Plot final L_PDE vs SRF for MC and GHB on shared axes (→ Fig. 8). The blow-up points visually identify both factors of safety side by side. | EITHER |
| 46–47 | Step 5.3 — Failure-surface extraction From each converged critical state, compute γ_max on a fine 200×200 post-processing grid; the locus of peak shear strain is the failure surface — no trial circles needed. Plot MC and GHB surfaces on the same cross-section (→ Fig. 9). Confirm the compound mechanism (basal bedding-plane segment + exit through marl) matches the paper. This step is laptop-friendly — it’s forward passes only. | LAPTOP |
| 48 | Buffer + result lock Tabulate FOS_LEM, FOS_MC, FOS_GHB. Lock the headline numbers. Buffer for an SSR sweep that needed re-bracketing. | EITHER |

# Days 49–56 — Sensitivity, Ablation & Figures (Phase 6a)

Goal: pre-empt the questions every Q1 reviewer asks — how sensitive are your results, is the coupling necessary, is the result reproducible — and produce the full publication-quality figure set.

Split: the sensitivity/ablation runs are training-scale and belong on the lab PC; the figure assembly is pure Matplotlib and comes home to the laptop.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 49–50 | Step 6.2 — Physics & numerics sensitivity (OAT) One-at-a-time ±20% sweeps: coal-seam K_s, rainfall intensity (10/20/40 mm/hr), and marl GSI (40/50/60, re-deriving E_rm, m_b, s, a each time). Each is a fresh solve. Record FOS response for the tornado plot. | LAB PC |
| 51 | Ablation — one-way vs two-way coupling Re-run with Kozeny-Carman feedback OFF and compare FOS against the monolithic two-way result. This is where you publish the “one-way overestimates FOS by up to ~21.5%” number your framework is built to expose (→ Fig. 11). | LAB PC |
| 52 | Numerics + reproducibility Collocation-point convergence (N_PDE = 5k/10k/20k/50k — the PINN’s mesh-convergence analogue) and 5 random-seed runs reporting mean FOS ± 1 SD. Directly answers the “is it reproducible?” reviewer concern. | LAB PC |
| 53 | Tornado plot + sensitivity synthesis Assemble the OAT results into a single tornado plot (→ Fig. 12), bars ordered by sensitivity. Write the sensitivity narrative for the Discussion. | LAPTOP |
| 54–55 | Step 6.1 — Publication figure set Finalise all 8–12 figures: site map/cross-section (Fig. 1), architecture schematic (Fig. 2), domain (Fig. 3), convergence (Fig. 4), ψ fields (Fig. 5), displacement (Fig. 6), validation (Fig. 7), SSR convergence (Fig. 8), γ_max surfaces (Fig. 9), FOS bars (Fig. 10), coupling effect (Fig. 11), tornado (Fig. 12). Self-contained captions, axis units, colour bars. | LAPTOP |
| 56 | Figure review Read every figure as a reviewer would, cold. Fix unlabelled axes, missing units, illegible legends. Reviewers form first impressions from figures before reading a word. | LAPTOP |

# Days 57–60 — Buffer & Thesis Assembly

Goal: absorb accumulated slippage and assemble the thesis document itself (distinct from the journal manuscript, which the next 15 days handle). All laptop work.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 57 | Global buffer The single most important day in the plan. Something upstream will have slipped — a training cycle, an SSR re-bracket, a derivation error. This is where it gets absorbed without moving the finish line. | EITHER |
| 58–59 | Assemble thesis document Pull Introduction, Literature Review, Methodology, Results, Discussion, Conclusions into the thesis template. Insert figures and tables, wire up cross-references and the reference manager (Zotero/Mendeley). | LAPTOP |
| 60 | Internal read-through + supervisor handoff Full read for narrative coherence and that every objective stated in your proposal is answered in the results. Hand the complete draft to Dr. Islam. Day 60 done. | LAPTOP |

# Days 61–75 — Manuscript & Journal Submission (15 days)

The thesis and the journal manuscript are not the same artefact. The manuscript is tighter, structured to the IMRaD consensus for computational geotechnics, and built to survive peer review. This block converts the thesis content into a submission-ready paper and gets it out the door.

Hardware: this entire block is laptop work. No new computation — unless review feedback later demands a rerun, the lab PC is done. The one EITHER row is a precaution in case you decide to regenerate a figure at higher resolution.

| Day | Task & detail | Run on |
| --- | --- | --- |
| 61 | Confirm target journal & read its guide Lock the target (Computers and Geotechnics, IF ≈ 5.3, is the primary fit; Engineering Geology, which published the source paper, is the natural alternative). Read its Guide for Authors in full — length limits, figure format, reference style, structured-abstract rules. | LAPTOP |
| 62 | Title + abstract Finalise the title (“Physics-Informed Neural Networks for Coupled Hydro-Mechanical Slope Stability Analysis: Mohr-Coulomb vs Hoek-Brown Comparison at an Open-Pit Lignite Mine”). Write the ≤250-word abstract: Problem → Method → Key results → Significance, with the two headline numbers in the last two sentences. | LAPTOP |
| 63 | Introduction 2–3 pages: slope-stability challenge with Işıkdere as motivator; LEM and FEM limitations; PINNs as mesh-free alternative; the explicit gap (no MC-vs-GHB comparison within a coupled PINN-SSR framework); bulleted objectives. | LAPTOP |
| 64 | Study site & data 2 pages: mine description citing Ulusay et al. (2014); extracted geotechnical/hydrogeological parameters (your Phase-1 table); derived parameters with methods cited step by step. | LAPTOP |
| 65–66 | Methodology 5–6 pages, your principal contribution — largely portable from the thesis draft you started on Day 26: governing equations, two-way monolithic coupling, architecture & loss, non-dimensionalisation, Adam→L-BFGS+GradNorm, SSR for MC and GHB with γ_max surface extraction. | LAPTOP |
| 67–68 | Results 4–5 pages: training convergence; baseline HM validation; MC-SSR vs GHB-SSR FOS; failure-surface comparison; effect of HM coupling. Reference figures in order; keep prose to what the figures don’t already say. | LAPTOP |
| 69 | Discussion 2–3 pages: when the MC-vs-GHB choice matters (confinement, geometry, rock-mass quality); one-way vs two-way safety implications; efficiency vs FEM; limitations (plane-strain, single section, no progressive failure) and future work. | LAPTOP |
| 70 | Conclusions + abstract reconciliation 1 page restating the 3–4 headline numbers with significance, no new material. Re-read the abstract against the finished results and align the numbers exactly. | LAPTOP |
| 71 | References, formatting, figure/table placement Apply the journal’s reference style via your manager. Verify every citation resolves. Format figures/tables to the journal’s spec; check resolution requirements (often 300–600 dpi). | LAPTOP |
| 72 | Optional high-res figure regeneration If the journal demands higher dpi or vector formats than you exported, regenerate. The laptop can do this for most figures; use the lab PC only if a field plot needs re-rendering from a heavy checkpoint. | EITHER |
| 73 | Self-review + length trim Read the whole manuscript cold against the journal’s length budget. Trim over-writing (each section >30% over budget is a warning sign). Check every claim is supported by a figure, table, or citation. | LAPTOP |
| 74 | Supervisor review + co-author sign-off Send to Dr. Islam, incorporate edits. Prepare submission extras: cover letter stating the novelty, suggested reviewers, highlights, graphical abstract, data-availability statement, author contributions. | LAPTOP |
| 75 | Submit Create the Editorial Manager / journal account, upload manuscript, figures, cover letter, and supplementary files. Complete the metadata. Submit. Save the manuscript number. | LAPTOP |

# Practical notes for the two-machine setup

## Keep the two machines in sync with Git

- One repository, cloned on both machines. Author and debug on the laptop; pull on the lab PC and run. Never edit code on the lab PC mid-run — it desynchronises the repo and you lose track of which version produced which result.

- Tag the frozen baseline (Day 37) and the locked FOS results (Day 48) in Git. When a reviewer asks “which configuration produced Fig. 9?” eight months from now, the tag answers instantly.

- Store large checkpoints outside Git (they bloat the repo) — use the lab PC’s disk plus one backup. Keep a small text manifest in the repo mapping each checkpoint to its config and result.

## Working while the GPU runs

- Long lab-PC runs are unattended time. The plan deliberately overlaps Methodology writing (Days 26–27) with training so the GPU hours aren’t dead time for you.

- Use tmux or nohup (Linux lab PC) or a persistent session so a dropped connection doesn’t kill a multi-hour run. Checkpoint every few thousand epochs so you can always resume.

- Log per-term losses to a file, not just the console. You’ll diagnose convergence from the laptop by reading those logs without occupying the GPU.

## What the laptop genuinely cannot do — and the workaround

The MX450’s 2 GB VRAM is the hard wall. Full-scale coupled training, SSR sweeps, and sensitivity runs will not fit — attempting them returns CUDA out of memory almost immediately. There is no laptop workaround that preserves the full problem; shrinking it enough to fit (a 2-layer net, N_PDE ≈ 500) destroys the accuracy you need. So the laptop’s role is firmly: derive, author, debug-at-toy-scale, post-process, and write.

- If the lab PC is ever unavailable: Google Colab (free tier gives a ~15 GB GPU; Colab Pro is cheap) can stand in for a training run. The same repo runs there unchanged. This is a useful fallback for a single urgent rerun during review.

- If the lab PC GPU turns out weaker than assumed: the Phase-4 and Phase-5 day counts stretch first, because they’re training-bound. Tell me the GPU model and VRAM and I’ll give you revised wall-clock estimates and, if needed, a reduced-scope configuration that still validates.

## Risk buffers — where the plan can absorb slippage

- Days 9, 24, 38, 48, 57 are explicit buffers. The Phase-3 (Day 24) and Phase-4 (Day 38) buffers are the ones you’re most likely to spend — architecture/coupling bugs and training non-convergence are the classic PINN time-sinks.

- If you reach Day 38 with training still not converged, that is the signal to escalate to your supervisor rather than burn the Phase-5 budget — a fundamentally mis-specified loss term is a science problem, not a scheduling one.

Tell me the lab PC’s GPU and I’ll convert the training blocks (Days 25–52) into concrete wall-clock estimates.